## BandMode config
| JSCARC/CLARC 2018 FD |  |  |  |  | W5RRR 12 F STX
SSB W5RRR Shack (Captain: Grimm/Jones/Hickman-GOTA)
[5 empty] | (D)aytime | [6 empty] | (N)ighttime | [6 empty] | Antenna | [5 empty] | Foot sw | 1st op Headset w/ mic | 2nd op Headset | 3rd op trainer headset | Headset 4ch mux | Audio adapters | Triplexer | BP Filter | Coax jumpers | Coax | Radial | Radio Manual | Comments
| Station | Rig | Owner | Mode | [14 empty] | TH7DX | 40m | 6m Yagi | G5RV | Shunt | [5 empty] | 1/4" to 3.5mm
[5 empty] | 6 | 10 | 15 | 20 | 40 | 80 | 160 | 6 | 10 | 15 | 20 | 40 | 80 | 160 | Yagi | Noodle |  |  | Fed
PRIME | 1 | TS-950 | JSCARC | SSB |  |  |  | X | [6 empty] | X |  |  |  | D | [5 empty] | Use cheapos? | need to verify that we have enough |  | 25 |  | x | 15m | x |  |  |  | OK w/ G5RV for 80?
PRIME | 2 | IC-9100 | W9TWJ | SSB |  |  |  |  | ~7.3 | [6 empty] | ~7.3 |  |  |  | D/N |  |  |  |  | Use cheapos? |  |  | 25 |  | x | 20m | x
PRIME | 3 | IC-781 | JSCARC | SSB |  |  | X | [9 empty] | X |  | D |  |  |  | N |  | Use cheapos? |  |  | 25
PRIME | 4 | IC-746 | W9TWJ | SSB |  | X | [11 empty] | X |  |  |  | N
PRIME | 5 | FT-100D | JSCARC | SSB/CW | X | [15 empty] | D
GOTA | K5HOU | FT1000D | JSCARC | SSB |  | A | B |  | C~7.2 | [6 empty] | ~7.2 | X |  | D |  |  | D |  |  | Use cheapos? |  |  | 25 |  | x | 10m | x |  | Restring 160m radial
SAT Shack (Captain: Maca)
[5 empty] | Daytime | [6 empty] | Nighttime | [6 empty] | Antenna | [5 empty] | Foot sw | 1st op Headset w/ mic | 2nd op Headset | 3rd op trainer headset | Headset 4ch mux | Audio adapters | [6 empty] | Comments
| Station | Rig |  | Mode | [14 empty] | Sat Yagi's | [10 empty] | 1/4" to 3.5mm
[5 empty] | 2/70cm | [6 empty] | 2/70cm
| 1 | TS-2000x | JSCARC | FM/SSB/CW | X | [6 empty] | X | [6 empty] | X | [5 empty] | N/A | Use cheapos? | Need to verify that we have enough |  | 25
DIGITAL Bluebonnet Pavilion (Captain: Fretz)
[5 empty] | Daytime | [6 empty] | Nighttime | [6 empty] | Antenna | [5 empty] | Foot sw | 1st op Headset w/ mic | 2nd op Headset |  | Headset 4ch mux | Audio adapters | [5 empty] | Ext Monitor | Comments
| Station | Rig | Owner | Mode | [14 empty] | N6BT V8 | T2FD | G5RV | Multi-Dipole MFJ 2289 | 6m Par | [7 empty] | 1/4" to 3.5mm
[5 empty] | 6 | 10 | 15 | 20 | 40 | 80 | 160 |  | 10 | 15 | 20 | 40 | 80 | 160
PRIME | 1 | TS-2000x | K5DLF | PSK/RTTY |  |  |  | X | [6 empty] | X |  |  |  | X |  |  |  |  | 100' 213 |  | N/A | Use cheapos? | Are HS required for digi?
PRIME | 2 | IC-746 PRO | K5KGH | PSK/RTTY |  |  |  |  | X | [6 empty] | X | [5 empty] | X |  |  |  | N/A | Use cheapos? | Are HS required for digi?
PRIME | 3 | FT-857D | N5FWB | PSK/RTTY |  |  | X | [10 empty] | X |  | X | [5 empty] | N/A | Use cheapos? | Are HS required for digi?
PRIME | 4 | TS-2000x | KB5PGY | PSK/RTTY | X | X | [10 empty] | X |  |  |  | X |  | X |  |  | N/A | Use cheapos? | Are HS required for digi?
CW Live Oak Pavilion (Captain: Lee)
[5 empty] | Daytime | [6 empty] | Nighttime | [6 empty] | Antenna | [5 empty] | Foot sw | 1st op Headset | 2nd op Headset | Audio adapters | Audio splitter adapter | Paddle | Triplexer | BP Filter | Coax jumpers | Coax | Radial | Ext Monitor | Comments
| Station | Rig | Owner | Mode | [14 empty] | Hex + Crankup Trailer | 40m Zepp | 80m Zepp | 160m L + Tuner | [5 empty] | 1/4" to 3.5mm
[5 empty] | 6 | 10 | 15 | 20 | 40 | 80 | 160 | 6 | 10 | 15 | 20 | 40 | 80 | 160
PRIME | 1 | IC-775 | W5OC | CW |  |  |  | X | [6 empty] | A |  | B |  | X |  | X |  |  |  | N/A | Bringing own-w5oc | TBD |  |  | Straight Dual paddle Single paddle? | x | 20m | x | 150' for hex |  |  | For all stns: Need to verify N3FJP CW config
PRIME | 2 | FT-1000MP | W5OC | CW |  |  |  |  | X | [6 empty] | X |  |  |  | X |  |  |  |  | N/A | Bringing own-w5oc | TBD |  |  | Straight Dual paddle Single paddle? |  | 40m | x | 150' for 40m
ROVER | 3 | TS-2000 | W5OC | CW |  | X | X | [10 empty] | X | X |  |  | X |  |  | N/A | Bringing own-w5oc | TBD |  |  | Straight Dual paddle Single paddle? | x | 15m | x | 150' for 80m
SOLAR STATION (Captain: Steward)
[5 empty] | Daytime | [6 empty] | Band (m) | [6 empty] | Antenna | [5 empty] | Solar Cells | Gell cells | [10 empty] | Comments
| Station | Rig |  | Mode
| 1 | FT-857D | N5FWB | ALL/ANY | * Jerry's choice - only need 5 contacts

## Event times
W5RRR 13 F STX

## signups
| JSCARC/CLARC 2018 FieldDay |  | as of 06/15/18
Signup Sheet
|  |  | Friday | Saturday |  |  | Sunday |  |  |  | Operating Preference
|  |  | 2018-06-22 | 2018-06-23 |  |  | 2018-06-24
Shift or Partial-shift you want to work?
|  |  | Setup 1 | Setup 2 | Afternoon | Early PM | Graveyard | Morning | Afternoon | Cleanup | Mode
| Name | Call | 5p-8p | 8a-11a | 1-6 p | 6p-12a | 12a-7a | 6a-10a | 10a-1p | 1p-2p | SSB | Digital | CW | SAT | GOTA
| Keith Grimm | KG5HOK | x | x | S | S |  | S | S | x
| David Lee | W5OC | x | x | C | C | C | C | C | x |  |  | x
| Ken Goodwin | K5RG |  |  |  | C |  |  | C |  |  |  | x
| Tanner Jones | N9TWJ | x | x | S | S | S | S | S | x | x |  |  |  | x
| David Fretz | K5DLF |  | x | D | D | D | D | D | x | x
| David Fanelli | KB5PGY |  | x | D |  |  | D | D | x | x | x
| Stu Donnan | W4STU |  | x | S | S | D | S | D | x | x | x |  | x
| MIke McCann | WA5SQD |  |  | S
| John Maca | AB5SS |  | x | X | X | X | X | X | x
| Jerry Steward | N5FWB |  | x | D | D | D | D |  |  |  | x |  | x
| Christi Evans | KG5NQP |  |  | S | S | S | S | S | x
| Keith Brandt | WD9GET |  | x | D
| Bob Logan | NZ5A |  |  | C | C | C | C | C | x
| Jessica Logan | KD5EUL |  |  |  | S | S | S
| Andy McAllister |  |  | x | X | X | X | X | X
| Wayne Jonson | K5OB |  |  | S | S
| Kelvin Hickman | K5KGH
GOTA | Jack Wisbiski | KE8JVT |  |  |  |  | x | [7 empty] | x
GOTA | Fred Gimenes | KG5WNN | [12 empty] | x
GOTA | Joe Carpinelli | KG5VMC | [12 empty] | x
GOTA | David Kimbrell | KG5URA | x | x |  |  |  |  | x | x |  |  |  |  | x
GOTA | John Dusl | KG5ZVQ | [12 empty] | X
GOTA | John Barker | KG5ZOR | x |  |  | x |  | x |  | x | x |  |  |  | x
| Terry Moore | KG5TJT
| Mike Urich | KA5CVH
| Carl Kotila | WD5JRD
| Gary Grobe | KE5AMW
Levi
| John Patterson | KC5LAA
| Lee Spinner | KD5SQN
| George Fletcher | AD5CQ
| Bob Cooke | KA5RWC
| Curt Tallman | WB5UZZ
Wes Coleman
Gary Grobe
| Bob Scully | N9RCS
| Beth Scully | KG5PJP
Initial projectsion of distribution
|  | SSB |  |  | 6 | 6 | 3 | 5 | 3 |  | SHADED MEANS FULL CAPACITY
|  | Digital |  |  | 4 | 2 | 3 | 3 | 3
|  | CW |  |  | 2 | 3 | 2 | 2 | 3
|  | Sat |  |  | 2 | 2 | 2 | 2 | 2
| Wayne Johnson | K5OB |  |  | x | x

## Checklist
FD Checklist
Shelter/operating position
Chairs
Clocks
Fans
Clipboards
Pens, pencills, makers
Light for nightimte w/ yello bug bulb
Radio Equipment
Radio
B/U Radio
Radio/Computer i/f
Mic
Key
keyer
Headphones
Headphones splitter
Dummy load
SWR/ power meter
fuses
Antenna
B/U antenna
Rope
Antenna Tuner
Coax jumpers
Antenna Feedline and connectors
BP Filters
Triplexer
Soundcard i/f
Coax adapters
12V DC P/S
Extension cords
PC
Monitors
Logger SW
Foot switch
Masts/towers
Guy lines
Ground radials
Rotor
Rotor cable/controller
Copy of FCC license
Generators
Gasoline
Funnels
Personal items
Sleeping bag/pillow
Air mattress/cots
change of clothes
First aid/meds
insect repellent
Hat/sunglasses
Flashlight/lantern
2m HT
cooler w/ ice
Water and beverages of choice
Snacks for late nite
Camera w/ batteries
Tools
Cable ties
Wrenches/sockets
Pliers/cutters
Utility knife
Hammer/sledge
Matches
Electrical tape
Measuring tape
Duct tape
Tool bag w/ hand tools
Solder gun and solder
Drill w/ bits
Magnifying glass
Fence Post Hammer
Multimeter
General
Section list
Fire extinguisher
Rope launcher
Paper towels
Safety tape
Orange cones
Trash bags
FD Banners
FD public information
Certificates (GOTA)
Fencing
Paper plates and utensils
Special
Solar cells
Gel battery for charging
Public table

## Bonus
Bonus points
Actionee
1200 | 100pt x 12 transmitter / 100% Emergency Power | N/A
100 | Press Release to Local Media (submit copy) | Lee
100 | Physical location in public place | N/A
100 | Public Information Table | Lee
100 | Message to ARRL Section Manager/Emergency Coordinator (submit copy) | KB5PGY
100 | 10 messages originated, relay, received-delivered (submit copy) | KB5PGY
100 | 1 QSO via Satellite | AB5SS
100 | 5 QSOs on alternate power (Solar) * another transmitter must be turned off | N5FWB
100 | Copy W1AW (submit copy) | KB5PGY
100 | Educational-related activity | K5KGH
100 | Site visit by elected governmental official | AB5SS/KD5EUL/W9TWL
100 | Site visit by representative of an agency | W9TWJ/K5DLF- George Fletcher AD5CQ; Mike Ulrich KA5CVH
500 | GOTA operator(s) make 500 QSOs in blocks of 20 ea (1 op cannot exceed 100) | K5KGH
500 | GOTA coach during GOTA ops | K5KGH
100 | 5 participants <=18 years to complete at least 1 QSO ea (20 pts per opr) | K5KGH
100 | Social Media | W9TWJ
3500

## TTD 061218
TTD
|  | SSB | Digital | CW | Comments
To Buy List
| headphone splitters x4 (DONE) | X | NA | OPEN
| Headphones x3 (DONE) | GOTA? | X | OPEN
| antenna coax TBD feet | NA | X | X | Amazon
| rotor cable for hex | NA | NA | X | Amazon
| triplexer jumpers | X | NA | X | Amazon for SSB and CW Villages
| Dacron rope/cord | NA | X | X | Amazon
| Behringer HA400 headphone mixer | X | NA | NA | Amazon
| Headphone extensions for Behringer (Dlee may have some) | X | NA | NA | 1/4" - 3.5mm adapters x 4
| Rental - Fans? | NA | Keith 2 | OPEN | Jerry will bring 1. Overall enuf?
| Bug Spray | NA | OPEN | OPEN | Keith will supply
| Radial wire for 160 | X | NA | X | For 160m Shunt and L
General To Do
| Sign in Sheet | OPEN | OPEN | OPEN | Lee
| NEED Bonus Point Manager & LIST (see Bonus tab) | X |  |  | Assignments made
| FD Info handouts? or not? (operating sheets or public info table handouts?) | OPEN |  |  | Dave
| Dave/Keith - Have you notified Security on keeping Gate open | OPEN |  |  | Dave
| Flag/banner at Gilruth entrance and Villages | OPEN |  |  | Christi/Dave + hanging
| Messaging/info to Clubs Members (ops) | OPEN |  |  | Dave
| Messaging/info to Clubs Members (esp for New Licensed) | OPEN |  |  | Dave
| Finalize GOTA handling of Students + New Licensed | OPEN | OPEN |  | Kelvin
| Safety Officer concerns | OPEN |  |  | Kelvin
| Bring antenna/SWR analyzer | OPEN |  |  | Dave
| Distribute Cell phone #'s for Band Captains + Safety Ofc | OPEN |  |  | Dave/ Need to also post at each Village
| Tools + Multimeter + soldering irons + duct tape | OPEN |  |  | All
| Fencing + post hammer? | N/A | N/A | N/A
| Orange Cones + security tape | OPEN |  |  | Dave
| Preserve RV spot for K5KGH | OPEN |  |  | Kelvin + Cones
| Contingency plans/policy | OPEN | OPEN | OPEN | Tarp= Keith/Jerry/Dave
Food/Water/Ice
| Tanner; Big Ice Chest, water, | Tanner | Fretz | Lee | Cooler Fretz; Lee
| John; Trash Bags (39 gal Black, 55 gal clear (janitors closet) | John | John | John
| CLARC provides Dinner/BBQ | CLARC |  |  | Verified
| Snacks; nuts, chips, salsa, cookies | BYOJF | BYOJF | BYOJF | Bring Your Own Junk Food
| COFFEE!!!! | Tanner |  |  | Tanner big + thermos @ ea village
| Lunch Saturday B4 FD Start - TBD Pizza, Subs, Wings? | Keith |  |  | Keith logistics : JSCARC to buy
| Cooler/Ice & Water for Digital Village & CW Village |  | Open | Open | Ice from center, but need bottled H2O
| SUNDAY AM Breakfast | Keith |  |  | Keith Surprise Breakfast (Hope for Rudy's Tacos)
To Do for SSB Village
| Put up 6m beam from John / Remove HexBeam |  |  |  | Separate Coax direct to shack?
Install new version of FD Software (all computers really)
| Q. Keith - Patch Panel plans - move before/after FD? | NA |  |  | Install afterwards
General shack/room clean up
| IC-781 Stow & replace with IC-9100 from Tanner |  |  |  | We still need IC 781- worth installing fan?
Setup 6m Rig: FD-100D or Tanner’s IC-746
Fan for circulation? John to bring oscillating fan, just in case.
Generator; Tanner Honda 7000; run part time, whole time, gas?
| How to Log sats for FD and AMSAT FD |  |  |  | In work
Extra PCs as needed
GOTA interference plan/ test
Band-in-use signage / station
Install Triplexer for TH7DX- Lockout Linear Amps, please
Setup GOTA station and instructions/scripts
ARRL Phonetics + Sections sheets
Radials for 160m
Kleenex/paper towels
To Do for CW Village
Move trailer/tower over
Rigs; IC-775, FT-1000MP, TS-2000?
Antennas:
move/install HexBeam + TBD Rotor
string up 40m/80m dipoles (who has these? or need to build?)
160m dipole or Inv-L (Dave ?)
run coax
4 runs; who’s bringing
run power (extension cords & how many)
Fan(s)
Grounding (can we use building ground?)
Generator? Dave Honda’s ?
Desk lights? Pen/paper
Fishing pole
Monitors/Keyboards/Mice
Chairs/tables/cushions (gotta be comfortable)
CW Keys, K1EL keyers, computers, interfaces, Macros
Tuners for antennas
Radials for 160m
Kleenex/paper towels
To Do for Digital Village
Rigs:
Jerry’s Go Kit FT-857
Fanelli TS-2000
Kelvin IC-746 Pro
Fritz - TS-2000
string/install antennas
Tanner antenna 10-80
Kelvin bringing Vertical
Fanelli - Vertical
Dave Lee - ?
run coax (4 runs)
run power (need extension cords)
Fans
Desk lights? Pen/paper
Chairs/tables/cushions (gotta be comfortable)
Computers/Monitors/Keyboards/Mice
SW
Kleenex/paper towels
Generator/gas
| Misc | X
| Solar setup/plan | X
Satellite setup/plan

## How To Win
This year W5RRR/K5HOU can easily amass up to: 3500 bonus points alone
Last year W5RRR (5F-class) total combined score of only 2398 points
200 GOTA
800 SSB
How to Win | [11 empty] | 150 CW
150 Dig
Mode | QSO | Multi | Points | THE COMPETITION (High Scores)
SSB | 1500 | 1 | 1500
Digi | 600 | 2 | 1200 |  | ID | Call | Class | QSOs | SCORE | SEC | Comments
CW | 800 | 2 | 1600 | CLASS F | USA | W6YX | 7F | 5460 | 17420 | SCV | 1st Hi Score Class F USA
Sat | 100 | 1 | 100 |  | USA | W2GSB | 6F | 4438 | 16102 | NLI | 2nd Hi Score Class F USA
GOTA SSB | 500 | 1 | 500 |  | USA | N4FR | 5F | 1330 | 12870 | TN | 3rd Hi Score Class F USA
GOTA Digi | 0 | 2 | 0 |  | Texas | KN5RX | 5F | 1805 | 6674 | STX | 1st Hi Score Class F TX
GOTA CW | 0 | 2 | 0
|  |  |  | CLASS A | BVARC | KK5W | 8A | 3487 | 14058 | STX | 1st Hi Score ALL USA TX
|  |  |  | CLASS E | Central Texas DX | W5CT | 2E | 3792 | 12836 | STX | 2nd Hi Score ALL USA TX
Sub-total |  |  | 4900
Power Multi |  | 2 | 9800
Bonus |  |  | 3500
Totals | 3500 |  | 18200

## CW Antennas
| Need | Order
1. 40M Doublet | 66 feet | NA
2. 80M | 133 feet | 150
3 160M | 120 feet | 150
450 ohm LL | 120 feet + 100 feet
Dacron Cord | 500 feet | 400

## GOTA
Expected GOTA hams
Joe Carpinelli
Jack Wisbiski
Fred Gimenes
David Kimbrell
John Barker
John Dusl
Beth Lasater

## Rules
Click on Box